## Sheet1
Region: 5
Location: DE007
CSS # 32914
Maximo Work Order No.: 17312
Asset #: 1732
Date Issued: 4/29/22
Original Description:DE007-01 (2) Boiler's replacement Proposal
Repairs Needed:
S&S Mechanical is proposing the following removal and replacement of two 1000K BTU Fulton Boilers at 100 Ogletown Road, Newark Delaware Army Reserve Center building #1. S&S shall isolate system and remove the existing Fulton Pulse boilers each with a 1000k BTU rating. S&S shall reconfigure all gas and water piping, intake and exhaust duct to fit new Fulton Endura 1000K bolers. S&S shall reclaim all glycol and replinish the system once all boilers are installed and ready for operation. S&S will verify the system of fit and leaks. S&S shall remove and clean all job related materials and debris from the site. S&S shall connect all power and controls to new boilers and perform all operational checks and the commissioning of each new boiler with the assistance of the factory representatives. *Labor will be tracked daily, total cost could be adjusted at completion of project. (2) HAVC Technicians >$100 per hour x 12=$2,400 per day/$24,000 for the 10-day estimate job (2) Plumbers >$100 per hour x 12= $2,400 per day/$24,000 for the 10-day estimate job
RS Means Line Buildup and Labor Summary (Data Version 2017, Q4):
Quantity | Line Item Number | Description |  | Labor Hours | Labor Rate/Hr | Materials | Equipment | Total
-- | NA | Parts/Hotel/Per Diem in attached quote 891 |  | -- | -- | 101552.55 | -- | 101552.55
-- | NA | S&S Labor 4 people |  | 480 | 100 |  |  | 48000
-- | NA | CMI Administrative Oversite |  | 40 | 80 | -- | -- | 3200
Estimate Summary:
Labor Hours |  | Labor Cost | Material Cost | Equipment | Total Cost |  | CE Factor | Total Estimate
520 |  | 51200 | 101552.55 |  | 152752.55 |  | 106% | 161917.703
RECAP: APRIL BILLING $70,000.00
PHASE 1 - CMI PAYING $70,000.00 DEPOSIT (INVOICE ATTACHED) LEAVES REMAINING BALANCE DUE UPON COMPLETION $91,917.70